## Sheet1
DOWNTON NEIGHBOURHOOD PLAN - Level 1 TASKS & OBJECTIVES
|  | 2014 |  |  | 2015
TASK | OWNER | OCT | NOV | DEC | JAN | FEB | 6/3 | 13/3 | 20/3 | 27/3 | 3/4 | 10/4 | 17/4 | 24/4 | 1/5 | 8/5 | 15/5 | 22/5 | 29/5 | 5/6 | 12/6 | 19/6 | 26/6 | 3/7 | 10/7 | 17/7 | 24/7 | 31/7 | 7/8 | 14/8 | 21/8 | 28/8 | 4/9 | 11/9 | 18/9 | Sept - Dec
Sign-off Qualitative survey | St G
Complete Sustain'by doc (Enfusion) | ID (Res G)
Mgmt Summary for Sustain'by report | ID (Res G)
Review Village Design Statement | ID (Res G)
Identify main headings for NP | ID (Res G)
Develop Quantitative survey | Vision G
Review Qual Survey prior to print run | Vision G
Sign-off funding for Leaflet print & delivery | Dave M
Deliver Quantitative survey | Eng. G
Publicise survey | Eng. G
Provide Survey help desk, lge print version, etc | Eng. G
Conclude Survey & collect returns | Eng. G
Draft of Outline N-Plan | ID (Edit G)
Prepare version 1 of Draft N-Plan | ID (Edit G)
Review V1 Draft N-Plan | ID (Edit G)
Fill identified gaps in draft N-Plan | Edit G | [5 empty] | 5/3
Confirm Policies and Proposals | Edit G | [5 empty] | 5/3
Outline Plan to Sarah Hughes(Wilts CC) | Edit G
Draft Plan to Parish Clerk | Parish C | [5 empty] | 5/3
Draft Plan to full Parish Council | Parish C | [6 empty] | 9/3
Special Steering Cttee meeting | St. G | [7 empty] | 17/3
Policies & Proposals agreed by Housing Cttee | Parish C | [7 empty] | 18/3
P&P: Housing Cttee recommends to full PC | Parish C | [8 empty] | 23/3
Editorial Group mtg | Edit G | [8 empty] | 27/3 |  |  | mid april |  |  | may |  |  |  |  | june |  |  | july |  |  |  |  | Aug
Prepare version 2 Draft N-Plan | Edit G. | [12 empty] | 22/4
Consult w. Parish C., business, et al. | Edit G. | [12 empty] | 22/4
Sust'y Appraisal quote from Enfusion | Ian D
Complete Sustainability Assessment | t.b.d. | [28 empty] | still u/k
Finalise V2 of N-Plan | Edit G. | [13 empty] | 29/4
Complete Consultation statement | Eng G. | [13 empty] | 29/4
Public consultation = 6 weeks | Eng G. | [14 empty] | 2/5 |  |  |  |  | 13/6
Review comments and make changes | Eng G. | [23 empty] | 10/7
complete table of changes for Con St | Eng G. | [24 empty] | 17/7
St Group recommends site preferences | St. G
develop site pref criteria | new Wk G.
St Group recommends site preferences | St G | [28 empty] | 16/8
PC agrees site criteria | PC | [29 empty] | 17/8
indepedent scoring of sites | Ind | [29 empty] | 19/8
notify landowners, developers, PC and WC of result | Eng G. | [29 empty] | 21/8
open meeting to share with residents | Eng G | [30 empty] | 22/8
review consultation statement | Eng G
final draft to St Gp to agree | Ed G | [31 empty] | 3/9
Draft for formatting | St G. | [31 empty] | 4/9
final draft to PC to agree | PC | [32 empty] | 14/9
Submit N-Plan to Wilts CC | Chair | [32 empty] | 15/9
Plan inspected by Wilts CC | WC
Relevent changes made | WC
Incentivise Residents to vote in Referendum | Eng G
legende |  | = completed |  |  |  |  | = complete / to do
= possibly overdue